## Test Cases
Test ID | Module | Test Case | Test Type | Technique | Preconditions | Test Data | Expected Result | Actual Result | Status | Bug ID | Evidence
TC-LOGIN-01 | Login | Login with valid credentials | Positive | Functional | User is on SauceDemo login page | standard_user / secret_sauce | User logs in successfully and reaches Products | User logged in successfully and reached Products | PASS
TC-LOGIN-02 | Login | Login with invalid password | Negative | Functional | User is on login page | standard_user / wrongpassword | Login is blocked and an authentication error is displayed | Login blocked. Message: "Epic sadface: Username and password do not match any user in this service." | PASS
TC-LOGIN-03 | Login | Login with empty username | Negative | Equivalence Partitioning | User is on login page | Username: blank / Password: secret_sauce | Login is blocked and username-required message is displayed | Login blocked. Message: "Epic sadface: Username is required." | PASS
TC-LOGIN-04 | Login | Login with empty password | Negative | Equivalence Partitioning | User is on login page | Username: standard_user / Password: blank | Login is blocked and password-required message is displayed | Login blocked. Message: "Epic sadface: Password is required." | PASS
TC-LOGIN-05 | Login | Login with locked-out user | Negative | Functional | User is on login page | locked_out_user / secret_sauce | Login is blocked and locked-out message is displayed | Login blocked. Message: "Epic sadface: Sorry, this user has been locked out." | PASS
TC-PROD-01 | Products | Verify product catalog display | Positive | Functional | User is logged in as standard_user | Standard product catalog | Products display with name, image, description, price and Add to Cart control | Six products displayed; each had name, image, description, price and Add to Cart | PASS
TC-PROD-02 | Products | Sort products by Name (Z to A) | Positive | Functional | User is on Products page | Sort: Name (Z to A) | Product order changes to descending alphabetical order | Order changed. First: "Test.allTheThings() T-Shirt (Red)"; Last: "Sauce Labs Backpack" | PASS
TC-PROD-03 | Products | Sort products by Price (low to high) | Positive | Functional | User is on Products page | Sort: Price (low to high) | Products are ordered from lowest to highest price | Order changed; lowest price shown first: $7.99 | PASS
TC-PROD-04 | Products | Sort products by Price (high to low) | Positive | Functional | User is on Products page | Sort: Price (high to low) | Products are ordered from highest to lowest price | Order changed; highest price shown first: $49.99 | PASS
TC-PROD-05 | Products | Open product details | Positive | Functional | User is on Products page | Sauce Labs Backpack | Details page displays name, image, description, price, Add to Cart and Back to Products | All listed elements displayed; product details matched the catalog | PASS
TC-CART-01 | Shopping Cart | Add product to cart | Positive | Functional | User is on Products page | Sauce Labs Backpack | Selected product is added and cart badge shows 1 | Sauce Labs Backpack added; cart badge showed 1 | PASS
TC-CART-02 | Shopping Cart | Verify product information in cart | Positive | Functional | Sauce Labs Backpack is in cart | Sauce Labs Backpack | Name, price and quantity match the product listing; Remove control is available | Name, price and quantity matched; Remove button was present | PASS
TC-CART-03 | Shopping Cart | Remove product from cart | Positive | Functional | Sauce Labs Backpack is in cart | Remove | Product is removed and cart becomes empty | Product disappeared; cart badge disappeared; cart was empty; Continue Shopping and Checkout remained | PASS
TC-CART-04 | Shopping Cart | Continue Shopping and re-add product | Positive | Functional | Cart is empty | Sauce Labs Backpack | Continue Shopping returns to Products; product can be added again | Returned to Products; product added again; cart badge 1; product visible in Cart | PASS
TC-CART-05 | Shopping Cart | Attempt to add the same product twice | Negative | Exploratory | User is on Products page | Sauce Labs Backpack x2 | If multiple quantities are supported, quantity should increase; otherwise behavior should remain consistent with the app design | Second add did not create a second line item; existing product was retained. No defect classified without a requirement | OBSERVATION
TC-CHECKOUT-01 | Checkout | Checkout with valid information and review overview | Positive | Functional | Sauce Labs Backpack is in cart | Yahoska / Conrado / 12345 | Checkout: Overview displays product and correct order totals | Overview opened; Backpack $29.99; Item total, Tax and Total displayed; Total $32.39 | PASS
TC-CHECKOUT-02 | Checkout | Complete valid order | Positive | End-to-End | Checkout: Overview with valid order | Sauce Labs Backpack | Order completes successfully and confirmation is displayed | Order completed. "Thank you for your order!" displayed; dispatch message shown; Back Home and Generate PDF order available | PASS
TC-CHECKOUT-03 | Checkout | Required field validation - Last Name missing | Negative | Functional | User is on Checkout: Your Information | First: Yahoska / Last: blank / ZIP: 12345 | Checkout should not continue when a required field is blank | Checkout did not continue | PASS
TC-CHECKOUT-04 | Checkout | Required field validation - First Name missing | Negative | Functional | User is on Checkout: Your Information | First: blank / Last: Conrado / ZIP: 12345 | Checkout should not continue when a required field is blank | Checkout did not continue | PASS
TC-CHECKOUT-05 | Checkout | Required field validation - ZIP missing | Negative | Functional | User is on Checkout: Your Information | First: Yahoska / Last: Conrado / ZIP: blank | Checkout should not continue when a required field is blank | Checkout did not continue | PASS
TC-CHECKOUT-06 | Checkout | Invalid ZIP format - alphabetic characters | Negative | Equivalence Partitioning | Sauce Labs Backpack is in cart | ZIP: ABCDE | Invalid ZIP format should be rejected with a validation message | ABCDE was accepted; no error shown; user could continue to Overview and Finish | FAIL | BUG-001 | BUG-001-ZIP.png
TC-CHECKOUT-07 | Checkout | ZIP boundary - 1 digit | Negative | Boundary Value Analysis | Sauce Labs Backpack is in cart | ZIP: 1 | ZIP with invalid length should be rejected | Continue was allowed | FAIL | BUG-001
TC-CHECKOUT-08 | Checkout | ZIP boundary - 4 digits | Negative | Boundary Value Analysis | Sauce Labs Backpack is in cart | ZIP: 1234 | ZIP with invalid length should be rejected | Continue was allowed | FAIL | BUG-001
TC-CHECKOUT-09 | Checkout | ZIP boundary - 5 digits | Positive | Boundary Value Analysis | Sauce Labs Backpack is in cart | ZIP: 12345 | Valid five-digit ZIP format should be accepted | Continue was allowed | PASS
TC-CHECKOUT-10 | Checkout | ZIP boundary - 6 digits | Negative | Boundary Value Analysis | Sauce Labs Backpack is in cart | ZIP: 123456 | ZIP with invalid length should be rejected | Continue was allowed | FAIL | BUG-001
TC-CHECKOUT-11 | Checkout | Special characters in name fields | Negative | Equivalence Partitioning | Sauce Labs Backpack is in cart | First: @@@ / Last: ### / ZIP: 12345 | Clearly invalid name input should be rejected if name format validation is required | Input was accepted; no error shown; user could reach Checkout: Overview | OBSERVATION
TC-CHECKOUT-12 | Checkout | Checkout with empty cart | Negative | Business Rule / Negative Testing | Cart contains no products | First: Yahoska / Last: Conrado / ZIP: 12345 | User should not be able to complete an order with no products | Overview showed no products; Item total $0.00, Tax $0.00, Total $0.00; Finish was enabled and order completed | FAIL | BUG-002 | BUG-002-Empty-Cart.png
TC-NAV-01 | Navigation | About external link | Positive | Functional | User is in SauceDemo menu | About | About link opens the intended external Sauce Labs site | Redirected to https://saucelabs.com/; browser Back returned to SauceDemo | PASS

## Summary
SauceDemo QA Testing — Test Execution Summary
Metric | Value | Bug ID | Description
Total Test Cases | 28 | BUG-001 | Invalid ZIP Code formats accepted
PASS | 21 | BUG-002 | Order can be completed with empty cart
FAIL | 5
OBSERVATION | 2
Confirmed Bugs | 2 | Testing Approach
Manual Functional Testing
|  | Techniques | Exploratory; Positive; Negative; Boundary Value Analysis; Equivalence Partitioning
Environment |  | Scope | Login, products, cart, checkout, order completion, basic navigation
Application | SauceDemo | Source | https://www.saucedemo.com/
Browser | Google Chrome
Device | Laptop
OS | Windows